## Project Budget
Budget: Project Plant Pals Operations & Training
TARGET BUDGET
86900
| LABOR |  |  | MATERIALS |  | FIXED COST | BUDGET
MILESTONES & TASKS | EMPLOYEE | HOURS | RATE | UNITS | $/UNIT(S)
Milestone 1: Project Initiation
Task 1: Requirement Gathering (Client needs, user expectations) | HR Specialist | 48 |  | 2 | 15000 |  | 30000
Task 2: Stakeholder Meetings (Logistics team, customers, admins) | HR Specialist | 30 |  | 1500 | 2 |  | 3000
Task 3: Feasibility Study (Cost, timeline, technology) | Delivery Drivers | 160 | 15 |  |  |  | 2400
Task 4: Approval & Sign-off | Delivery Drivers | 53 | 15
[6 empty] | Total | 35400
Milestone 2: UI/UX Design
Task 1: User Research (Courier staff, customers, admins) | HR | 20 |  |  |  | 15000 | 15000
Task 2: Wireframing | Developers
Task 3: Prototype (Figma/Adobe XD) | Developers
[6 empty] | Total | 15000
Milestone 3: Frontend Development (Web/Mobile App)
Task 1 : Project Setup (React/Flutter) | HR Specialist | 10 | 50 |  |  |  | 500
Task 2 : Authentication Module (Login, Roles: Admin/Courier/Customer) | Training Manager | 80 | 25 |  |  |  | 2000
Task 3 : Order Placement & Tracking | Training Manager | 80 | 25 |  |  |  | 2000
[6 empty] | Total | 4500
Milestone 4: Backend Development
Task 1 : Database Design | HR Specialist | 80 | 50 |  |  |  | 4000
Task 2 : Authentication APIs | Training Manager | 80 | 25 |  |  |  | 2000
Task 3 : Order Management APIs (Create, Update, Track) | Training Manager | 80 | 25 |  |  |  | 2000
[6 empty] | Total | 8000
Milestone 5: Integration & Testing
Task 1 : API Integration (Frontend-Backend) | HR Specialist | 80 | 50 |  |  |  | 4000
Task 2 : Unit Testing | Training Manager | 80 | 25 |  |  |  | 2000
Task 3 : UI Testing (Cross-browser/device) | Training Manager | 80 | 25 |  |  |  | 2000
[6 empty] | Total | 8000
Milestone 6: Deployment
Task 1 : Cloud Setup (AWS/Azure/Google Cloud) | HR Specialist | 80 | 50 |  |  |  | 4000
Task 2 : CI/CD Pipeline (GitHub Actions/Jenkins) | Training Manager | 80 | 25 |  |  |  | 2000
Task 3 : Production Release | Training Manager | 80 | 25 |  |  |  | 2000
[6 empty] | Total | 8000
Milestone 7: Maintenance & Support
Task 1 : Bug Reports | HR Specialist | 80 | 50 |  |  |  | 4000
Task 2 : System Updates | Training Manager | 80 | 25 |  |  |  | 2000
Task 3 : Performance Monitoring | Training Manager | 80 | 25 |  |  |  | 2000
[6 empty] | Total | 8000
Reserve buffer | [6 empty] | 3100
TOTAL | [6 empty] | 86900