## Sheet1
Change Control Log
[5 empty] | Impact |  |  | Date
# | Date | Requestor | Subject | Scope | Cost | Time | Approved | Plan updated | Closed
1 | 2025-07-11 | Client | Automated Route Optimization | AI integration | $15,000 | 3 weeks | Yes | 2025-07-18 | 2025-07-18
2 | 2025-07-25 | Client | Add Delivery Time Slot Selection for customers during checkout. | Checkout UI update | $8,000 | 2 weeks | Yes | 2025-08-03 | 2025-08-03